## Phases Overview
Overview of Phases
Phase 1: Planning and Benchmarking (Pre-Migration)
Back up everyting: Not required - Site already live
Document Baseline Analytics: Record current analytics, conversion rate, and and top-performing pages.
Set up staging: Already done by development team
Implement content freeze
Phase 2: Technical and SEO Preparation
Map your 301 Redirects
Set up canonical tags
Set up Robots.txt
Set up Sitemap
Prepare DNS and SSL
Phase 3: Launch Day
Execute redirects
Test functionality and mobile friendliness | Mobile performance to be checked - We've already detected issues.
Reconnect tracking tags
Instruct Google of domain change
Set up / update Google Search Console
Implement and Submit new Sitemap | Sitemap to be altered based on feedback received from Brandon/Phil/Grant. Looking to change the current URL structures, since most contain /home/
Implement Robots.txt | Sub-domains can't be included in main site robots. noindex to be implemented.
Phase 4: Post-Migration Monitoring
Monitor 404 errors
Check page speed
Track traffic and rankings
Ensure www to non-www redirection
Ensure domain redirect
Implement canonical on the legacy website (classic.pggames) to tell search engines paradisegames.com is the correct URL.

## Checklist
Status | Task | Notes
Phase 1: Pre-Migration Planning
FALSE | Back up everyting: Ensure everyting is like-for-like on the new domain (already live)
TRUE | Document Baseline Analytics: Record current analytics, conversion rate, and and top-performing pages.
TRUE | Set up staging: Already done by development team
TRUE | Implement content freeze
TRUE | Benchmark current website performance - see GSC and GA4
TRUE | Benchmark backlink profile for pggames.com and paradisegames.com
TRUE | Benchmark positioning on SERPs through Ahrefs
Phase 2: Technical and SEO Preparation
TRUE | Map your 301 Redirects | TBC based on feedback from Grant/Phil/Brandon. Update - redirects have already been implemented, so this needs to be monitored.
FALSE | Set up canonical tags
TRUE | Set up Robots.txt | To be implemented
TRUE | Set up Sitemap | To be implemented
TRUE | Prepare DNS and SSL | Done by PG Games team.
Phase 3: Launch Day
TRUE | Execute redirects | Completed by the PG Games team on 16/07/2026
TRUE | Test functionality and mobile friendliness
TRUE | Reconnect tracking tags | Completed - Changed the Data Stream in Google Analytics. Also enabled cross-domain tracking.
TRUE | Instruct Google of domain change
TRUE | Set up / update Google Search Console
FALSE | Implement and Submit new Sitemap | See comments in Sheet 1
FALSE | Implement Robots.txt | See comments in Sheet 1
TRUE | www to non-www redirect | Completed by the PG Games Team on 16/07/2026
Phase 4: Post-Migration Monitoring
TRUE | Monitor 404 errors
TRUE | Check page speed | Page speed already impacted on the new domain (already live)
TRUE | Track traffic and rankings
TRUE | Ensure www to non-www redirection
TRUE | Ensure domain redirect
FALSE | Implement canonical on the legacy website (classic.pggames) to tell search engines paradisegames.com is the correct URL.
TRUE | Update Data Stream in Google Analytics.
TRUE | Set up Cross-Domain tracking in Google Analytics | "Without cross-domain measurement, new cookies with new IDs are created for each domain a user visits."
FALSE | GSC Instruction - Website Migration from pggames.com to paradisegames.com

## Backlink Benchmarking
https://paradisegames.com/ | pggames.com

## Performance Benchmarking
pggames.com
Ahrefs
Organic Traffic
# All Users
# Start date: 20260618
# End date: 20260715
Page title and screen class | Views | Active users | Views per active user | Average engagement time per active user | Event count | Key events | Total revenue
Home - Paradise Games | 370824 | 117501 | 3.1559 | 93.4433 | 1390885 | 0 | 0
Welcome Back - Paradise Games | 181126 | 27730 | 6.5318 | 50.1984 | 490825 | 0 | 0
Casino - Paradise Games | 156155 | 22314 | 6.9981 | 124.7379 | 453717 | 0 | 0
Results - Paradise Games | 110235 | 16368 | 6.7348 | 277.6004 | 327646 | 0 | 0
Lottery - Paradise Games | 57425 | 10169 | 5.6471 | 41.1107 | 157828 | 0 | 0
- Paradise Games | 51878 | 9817 | 5.2845 | 43.7853 | 169806 | 0 | 0
2 3 4 & 5 Ball Lotto - Paradise Games | 41521 | 8435 | 4.9225 | 528.7656 | 114859 | 0 | 0
Account - Paradise Games | 18856 | 4730 | 3.9865 | 63.4116 | 48534 | 0 | 0
Page Not Found - Paradise Games | 12923 | 1030 | 12.5466 | 92.4447 | 47864 | 0 | 0
Cashier - Paradise Games | 11418 | 2867 | 3.9826 | 75.9693 | 33562 | 0 | 0
Timed Out - Paradise Games | 10404 | 3506 | 2.9675 | 31.3597 | 30349 | 0 | 0
SportsBook - Paradise Games | 10075 | 1971 | 5.1116 | 16.3988 | 27764 | 0 | 0
Debit Card - Paradise Games | 3764 | 672 | 5.6012 | 171.6265 | 10854 | 0 | 0
Paradise 3 4 - Paradise Games | 3060 | 1342 | 2.2802 | 139.9955 | 8007 | 0 | 0
Promotions - Paradise Games | 1652 | 986 | 1.6755 | 41.2901 | 4389 | 0 | 0
Contact Support - Paradise Games | 1633 | 969 | 1.6852 | 38.9443 | 4125 | 0 | 0
Redeem Gift Card - Paradise Games | 1291 | 459 | 2.8126 | 104.1525 | 3791 | 0 | 0
Careers - Paradise Games | 1179 | 750 | 1.572 | 33.5787 | 2899 | 0 | 0
Paradise 5 - Paradise Games | 1108 | 494 | 2.2429 | 161.7166 | 3111 | 0 | 0
Kanoo - Paradise Games | 710 | 217 | 3.2719 | 51.2028 | 2097 | 0 | 0
Password Expired - Paradise Games | 553 | 247 | 2.2389 | 222.2551 | 1787 | 0 | 0
Borlette Lotto - Paradise Games | 546 | 296 | 1.8446 | 122.5608 | 1428 | 0 | 0
AboutUs - Paradise Games | 304 | 219 | 1.3881 | 37.516 | 861 | 0 | 0
TermsAndConditions - Paradise Games | 151 | 93 | 1.6237 | 69.5054 | 445 | 0 | 0
HowToPlay - Paradise Games | 117 | 85 | 1.3765 | 26.8706 | 366 | 0 | 0
Cookies - Paradise Games | 79 | 63 | 1.254 | 9.6508 | 232 | 0 | 0
FAQ - Paradise Games | 75 | 61 | 1.2295 | 21.8689 | 229 | 0 | 0
Privacy - Paradise Games | 66 | 55 | 1.2 | 22.6545 | 188 | 0 | 0
ResponsibleGambling - Paradise Games | 65 | 50 | 1.3 | 18.44 | 162 | 0 | 0
Server Error - Paradise Games | 36 | 24 | 1.5 | 8.6667 | 125 | 0 | 0
Forgot Password - Paradise Games | 26 | 14 | 1.8571 | 43.6429 | 104 | 0 | 0
Winning Numbers - Paradise Games | 25 | 5 | 5 | 33.8 | 62 | 0 | 0
Register - Paradise Games | 22 | 3 | 7.3333 | 253.3333 | 54 | 0 | 0
Login - Paradise Games | 4 | 1 | 4 | 53 | 8 | 0 | 0
Anonymous View (Beta) - Startpage - Private Search Engine. No Tracking. No Search History. | 1 | 1 | 1 | 0 | 4 | 0 | 0
aboutus - Paradise Games | 1 | 1 | 1 | 0 | 1 | 0 | 0
careers - Paradise Games | 1 | 1 | 1 | 0 | 1 | 0 | 0
- Jeux du Paradis | 0 | 1 | 0 | 235 | 13 | 0 | 0
- เกมสวรรค์ | 0 | 1 | 0 | 7 | 1 | 0 | 0
Accueil - Jeux Paradise | 0 | 7 | 0 | 351 | 79 | 0 | 0
Accueil - Paradise Games | 0 | 1 | 0 | 33 | 1 | 0 | 0
Anasayfa - Paradise Games | 0 | 1 | 0 | 55 | 1 | 0 | 0
Assistance téléphonique - Paradise Games | 0 | 1 | 0 | 167 | 1 | 0 | 0
Beranda - Paradise Games | 0 | 2 | 0 | 9 | 2 | 0 | 0
Bienvenue à nouveau - Paradise Games | 0 | 3 | 0 | 30 | 5 | 0 | 0
Carrières - Jeux Paradis | 0 | 1 | 0 | 0 | 2 | 0 | 0
Casino - Jeux de Paradis | 0 | 3 | 0 | 245.3333 | 20 | 0 | 0
Domov - Paradise Games | 0 | 1 | 0 | 2 | 1 | 0 | 0
Ergebnisse – Paradise Games | 0 | 1 | 0 | 30 | 1 | 0 | 0
Home - Giochi del Paradiso | 0 | 1 | 0 | 30 | 2 | 0 | 0
Inicio - Juegos del Paraíso | 0 | 6 | 0 | 28.5 | 11 | 0 | 0
Loterie - Jeux du Paradis | 0 | 1 | 0 | 266 | 30 | 0 | 0
Loto à 2, 3, 4 et 5 boules - Jeux du Paradis | 0 | 1 | 0 | 3816 | 31 | 0 | 0
Mot de passe expiré - Paradise Games | 0 | 1 | 0 | 871 | 14 | 0 | 0
Page introuvable - Paradise Games | 0 | 1 | 0 | 34 | 1 | 0 | 0
Paradise 3 4 - Jeux Paradise | 0 | 1 | 0 | 166 | 4 | 0 | 0
Paradise 5 - Jeux Paradise | 0 | 1 | 0 | 12 | 1 | 0 | 0
Paris sportifs - Jeux Paradise | 0 | 1 | 0 | 9 | 3 | 0 | 0
Promozioni - Paradise Games | 0 | 1 | 0 | 16 | 2 | 0 | 0
Página inicial - Paradise Games | 0 | 8 | 0 | 12.375 | 9 | 0 | 0
Résultats - Jeux du Paradis | 0 | 1 | 0 | 30 | 1 | 0 | 0
Résultats - Paradise Games | 0 | 3 | 0 | 228.3333 | 13 | 0 | 0
Sportweddenschappen - Paradise Games | 0 | 1 | 0 | 1 | 1 | 0 | 0
Startpagina - Paradise Games | 0 | 1 | 0 | 22 | 2 | 0 | 0
Welkom terug - Paradise Games | 0 | 1 | 0 | 1 | 1 | 0 | 0
Головна - Paradise Games | 0 | 1 | 0 | 35 | 1 | 0 | 0
الرئيسية - ألعاب بارادايس | 0 | 2 | 0 | 12.5 | 2 | 0 | 0
गोपनीयता - पैराडाइज़ गेम्स | 0 | 1 | 0 | 98 | 2 | 0 | 0
होम - पैराडाइज़ गेम्स | 0 | 1 | 0 | 126 | 2 | 0 | 0
হোম - প্যারাডাইস গেমস | 0 | 3 | 0 | 39.6667 | 4 | 0 | 0
คุกกี้ - พาราไดซ์เกมส์ | 0 | 1 | 0 | 11 | 1 | 0 | 0
หน้าหลัก - พาราไดซ์ เกมส์ | 0 | 52 | 0 | 31.5385 | 72 | 0 | 0
โปรโมชั่น - พาราไดซ์ เกมส์ | 0 | 1 | 0 | 17 | 1 | 0 | 0
ໜ້າຫຼັກ - ເກມ Paradise | 0 | 1 | 0 | 18 | 1 | 0 | 0
မူလစာမျက်နှာ - Paradise Games | 0 | 1 | 0 | 79 | 2 | 0 | 0
首页 - Paradise Games | 0 | 5 | 0 | 13.8 | 6 | 0 | 0